## Mujtaba Khan
Mujtaba Khan -- Sprint 01 / Lightgrid Energy
Validate with Mujtaba - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Zone A | SCRUM-38 | Lab Onboarding Checklist | Finalize checklist: data requirements, system access, customer qualification questions. Manish reviews for technical completeness. | 40/100 | Not Started | 2026-06-15 | Overdue. Critical before university pilot. Draft first, then review with Manish.
Infra | SCRUM-36 | CI/CD Pipeline Ownership | Take ownership of CI/CD deployment strategy. GCP deploy approach, branch strategy, automated test gates. | 28/100 | In Progress | 2026-06-28 | Mujtaba owns per Jun 25. Coordinate with Nishant who is pushing repos today/tomorrow.
Infra | SCRUM-39 | MLOps Pipeline (co-own w/ Nishant) | Model versioning, experiment tracking, dev to staging to prod promotion on GCP. Co-own with Nishant. | 18/100 | Not Started | 2026-07-15 | Define ownership split with Nishant first before build starts.
Infra | SCRUM-31 | Zone A-B Interface Contract (sign-off) | Formal sign-off once Manish + Nishant complete spec. Review and lock. Hard blocker on E2E test. | 10/100 | Not Started | 2026-06-28 | Manish drafts, Nishant co-signs from Zone B, Mujtaba final sign-off.
-- | -- | Jira Team Invites (BLOCKING) | Invite Rakshit, Nishant, Manish, Tilak, Krish to lightgrid-energy.atlassian.net. No team member has a Jira account yet. | 0/100 | Not Started | 2026-06-26 | BLOCKING everything. Must happen before sprint tracking can start. Send invites today.
-- | -- | Krish Redeployment Decision | DVFS + TCS deprioritized. Decide where Krish contributes: (A) Eval gate testing, (B) Zone B protocols MQTT/BACnet, (C) 50MW sim data prep. | -- | TBD | 2026-06-26 | Recommend Option B - Zone B protocols. Nishant overloaded and Krish has hardware/systems background.

## Manish Chauhan
Manish Chauhan -- Sprint 01 / Lightgrid Energy
Validate with Manish - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Infra | SCRUM-31 | Zone A-B Interface Contract (draft) | Define full API contract: endpoints, payload schema, error handling, telemetry return format. Nishant must co-sign from Zone B side. | 10/100 | Not Started | 2026-06-28 | CRITICAL - overdue Jun 12. Blocks E2E integration test (hard gate Jun 28). Priority #1 for Manish.
Zone A | SCRUM-33 | Decision Engine + Operator UI | Output format defined, basic rendering working. 3 audience views: Executive (risk profile, sign-off), Watcher/Facility Manager (config), Tenant (opt-in, savings). | 32/100 | In Progress | 2026-07-04 | 6 personas fully mapped per Granola. Wireframes in progress. RBAC groundwork with Nishant. Validate wireframe % tomorrow.
Zone A | SCRUM-34 | Tenant Surface | Flex-tier opt-in interface. Savings attribution display wired to AE output. Educational MVP demo for first pilots. | 20/100 | Not Started | 2026-07-04 | Depends on AE output format being locked first. Manish owns design.
Zone A | SCRUM-13 | Accountability Engine (arch review) | Review and validate dual-brain architecture: checklist/soul layer + MPC brain. 11 rules, 4 clusters (Know/Decide/Limit/Give Back). | 28/100 | In Progress | 2026-06-25 | Rakshit + Nishant building. Manish reviews architecture and signs off on design.
Zone B | -- | Auth / RBAC Groundwork | Role-based access control foundation for multi-tenant dashboard. Define role hierarchy: exec, operator, admin, tenant. Co-build with Nishant. | 15/100 | In Progress | 2026-07-04 | Mentioned in Granola. Define role hierarchy before UI build starts.

## Rakshit Mishra
Rakshit Mishra -- Sprint 01 / Lightgrid Energy
Validate with Rakshit - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Zone A | SCRUM-16 | Geo-shift RL Optimizer | Train geo-based RL pathway, validate + pass all 8 eval gates. ITransformer architecture. Physics equations integrated. | 42/100 | In Progress | 2026-06-25 | In progress. Policy-based, needs production upgrade. V1.5 training ongoing. Confirm gate pass status tomorrow.
Zone A | SCRUM-17 | Time-shift RL Optimizer | Train time-based RL pathway, validate against eval gates. 2-5 min ahead predictions, low latency. Outcomes: 31% lower peak, 27% lower carbon, 16% cheaper. | 42/100 | In Progress | 2026-06-25 | Parallel to geo-shift. Same gate requirements. Confirm % complete tomorrow.
Zone A | SCRUM-11 | Classifier | Flex-tier 0-3, priority scoring, tenant sensitivity, only-what-is-given enforcement. Hierarchical: critical / medium / flexible tiers. | 25/100 | R&D Phase | 2026-06-20 | Overdue. Tilak supporting. Move from R&D to build phase. Technical classification can be done now.
Zone A | SCRUM-12 | Rescheduler | Dispatch layer + trigger gates (grid signal, $/CO2 delta threshold, emergency). Trigger gate logic lives here - NOT in the optimizer. | 32/100 | In Progress | 2026-06-25 | Rakshit owns (corrected from Manish). MPC checklist layer as governance wrapper. Confirm approach tomorrow.
Zone A | SCRUM-13 | Accountability Engine (build) | 11 rules, 4 clusters. Dual-brain: soul/checklist layer always-on + MPC second brain 10-step lookahead. Co-build with Nishant. | 28/100 | In Progress | 2026-06-25 | Interesting architecture + thesis per Mujtaba. Hasti will expand later. Validate thesis completeness tomorrow.
Zone A | SCRUM-27 | Eval Framework (lead - all 8 gates) | Own gates 0-8: data quality, ML quality, physics compliance ASHRAE A1, calibration, generalization, decision quality, RL policy quality, numerical accuracy. | 50/100 | In Progress | 2026-06-23 | Rakshit main owner (corrected). V2 gates 1-4 built. ~2-3 hrs of tests remaining. Tilak supporting.
Zone A | SCRUM-30 | Load Classifications | 10/50/100 MW load profiles + flexibility tiers + ramp rates. 4 types: AI Training 50%, Inference 25%, Batch Analytics 15%, Checkpointing 10%. | 30/100 | In Progress | 2026-06-20 | Feeds directly into classifier. Benchmark sources: MLPerf, Alibaba cluster, BitBrains, Google Cluster.

## Nishant Raghuvanshi
Nishant Raghuvanshi -- Sprint 01 / Lightgrid Energy
Validate with Nishant - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Zone A | SCRUM-26 | Data Ingestion - Push to GitHub | All 3 pipelines (Grid APIs/weather, Facility telemetry, Workload traces) complete and pushed to GitHub. Verified against schema contract. | 72/100 | Needs GitHub | 2026-06-25 | Mujtaba confirms complete. Push target: today/tomorrow (Jun 25/26) per Granola. Validate commit is live.
Zone A | SCRUM-18 | AE Low-Fi Validator Loop | Dispatch -> AE validates -> recursive refinement until output passes -> passes to hi-fi DT. Threshold-based N runs. | 35/100 | In Progress | 2026-07-02 | Nishant owns (corrected). GCP pipeline being built - checklist + MPC versions in parallel. Tilak framed internal sim for this.
Zone B | SCRUM-19 | Historian Connector - Deploy-Ready | Confirm deploy-ready, push to GitHub. BMS/EMS/DCIM nodes, ingestion to GCP. Humber tag list verified. MQTT scope confirmed. | 80/100 | In Progress | 2026-06-14 | Pretty well done per Mujtaba. Overdue - confirm GitHub status. OPC UA first; MQTT scope after Humber meeting.
Zone B | SCRUM-20 | OPC UA Layer | Standard endpoints, master tag list integration, read/write validated end-to-end. Needs Humber to expose server URL, port, node structure. | 65/100 | In Progress | 2026-06-24 | ~70% per Mujtaba. TBD - confirm with team tomorrow. Coordinate Humber server access.
Zone B | SCRUM-21 | MQTT Plugin | Assess scope post-Humber, then implement + validate. Config-based framework template for DC types without DCIM. | 15/100 | Not Started | 2026-06-24 | Scope TBD after Humber meeting. Config template approach for MQTT-based DCs.
Zone B | SCRUM-22 | BACnet Plugin | Assess scope + implement + validate. Part of multi-protocol historian framework. | 15/100 | Not Started | 2026-06-24 | Same config-template approach as MQTT. Prioritize after OPC UA confirmed.
Zone B | SCRUM-23 | Modbus Plugin | Assess scope + implement + validate. | 15/100 | Not Started | 2026-06-24 | Third protocol in stack. Scope post-Humber interaction.
Zone B | SCRUM-24 | GCP Historian Deploy | Deploy + validate end-to-end on GCP. Zone A dispatches flowing into GCP time-series storage. | 65/100 | In Progress | 2026-06-20 | Overdue. Confirm deployment status tomorrow.
Zone B | SCRUM-25 | GCP Telemetry Return Path | Telemetry flowing from PLC/physical asset back to GCP. Latency measured and within budget. | 20/100 | Not Started | 2026-06-25 | Blocked on Humber OPC UA connection first. Architecture designed - needs physical endpoint.
Infra | SCRUM-31 | Zone A-B Interface Contract (co-sign) | Review + co-sign API contract from Zone B perspective. Confirm payload schema and telemetry return format. | 10/100 | Not Started | 2026-06-28 | Manish drafts, Nishant co-signs. Hard blocker on E2E test.
Infra | SCRUM-36 | CI/CD Pipeline (execution) | Push all remaining repos to GitHub. Repo structure, branch strategy per Mujtaba direction. | 28/100 | In Progress | 2026-06-25 | Mujtaba owns strategy. Nishant executes. Repos target: today/tomorrow.
Infra | SCRUM-39 | MLOps Pipeline (co-own w/ Mujtaba) | Model versioning, experiment tracking, dev to staging to prod on GCP. | 18/100 | Not Started | 2026-07-15 | Define ownership split with Mujtaba first.
Infra | SCRUM-35 | GCP Monthly Cost Estimate | Pull GCP monthly cost estimate, coordinate with Rakshit/Krish/Tilak on compute needs, send to Mujtaba. | 0/100 | Not Started | 2026-06-12 | Overdue since Jun 12. Quick task - pull from GCP console and send today.
Infra | -- | Internal Simulation 50MW (co-own w/ Tilak) | GCP pipeline for 50MW reference DC simulation. ERCOT-based, physics engine, workload graphs, full-stack E2E. | 32/100 | In Progress | 2026-07-25 | Co-own with Tilak. Tilak defines DC spec (task 1); Nishant builds GCP pipeline.

## Tilak
Tilak -- Sprint 01 / Lightgrid Energy
Validate with Tilak - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Zone A | SCRUM-30 | 50MW Reference DC - Task 1 (PRIMARY) | Define the 50MW reference DC simulation: solar/battery/asset mix, workload profiles, flexibility tiers, ramp rates. Foundation for internal simulator. | 30/100 | In Progress | 2026-06-20 | PRIMARY task per Granola. Send task 1 doc to Nishant ASAP. Nishant + Rakshit supporting on spec sheet.
Zone A | SCRUM-26 | Data Schema Contract | Define fields, types, validation rules for all 3 ingestion sources. Needed to formally verify Nishant data ingestion pipelines. | 40/100 | Not Started | 2026-06-14 | Overdue Jun 10. Coordinate with Nishant - ingestion complete but formal schema doc needed.
Zone A | SCRUM-27 | Eval Gates 1+2 (Rakshit leads, Tilak supports) | Data quality gate + physical out-of-bounds gate. These block the entire pipeline. | 50/100 | In Progress | 2026-06-20 | ~2-3 hrs of tests remaining. Rakshit leads. Gate 1+2 must pass before optimizer output reaches rescheduler.
Zone A | SCRUM-28 | Eval Gates 3+4 (support) | Overfit detection + per-variable accuracy gate. | 45/100 | Not Started | 2026-06-23 | Depends on gates 1+2 passing first.
Zone A | SCRUM-29 | Eval Gates 5+6 (support) | Latency budget gate + zero physics violations (ASHRAE A1 - most critical). | 40/100 | Not Started | 2026-06-23 | Physics compliance is the most important gate. All must pass before optimizer output is trusted.
Zone A | SCRUM-11 | Classifier (support - hierarchical jobs) | Support Rakshit on hierarchical job classification: critical/medium/flexible. 4 workload types (Training 50%/Inference 25%/Batch 15%/Checkpointing 10%). | 25/100 | R&D Phase | 2026-06-20 | Overdue. Move from R&D to build. Technical part can be done now.
Infra | SCRUM-32 | E2E Integration Test - HARD GATE | Full pipeline: ingestion -> classifier -> eval -> opt engine -> rescheduler -> AE -> historian -> OPC UA -> telemetry return. ALL gates passing. | 5/100 | Not Started | 2026-06-28 | HARD GATE. If this fails, lab deployment does not proceed. Nishant + Rakshit on-call to fix. Blocked on interface contract.
Infra | -- | Internal Simulation 50MW (co-own w/ Nishant) | Co-own with Nishant. Define reference DC specs (task 1) then validate full stack through simulation. | 32/100 | In Progress | 2026-07-25 | Tilak defines DC spec; Nishant builds GCP pipeline. ERCOT + physics-based. All eval gates must pass.

## Krish Patel
Krish Patel -- Sprint 01 / Lightgrid Energy
Validate with Krish - Jun 26 2026 ¦ Jira: lightgrid-energy.atlassian.net
Zone | Jira | Component | Requirement / Deliverable | Score | Status | Due Date | Notes for Validation
Zone A | SCRUM-14 | DVFS - DEPRIORITIZED | Dynamic voltage + frequency scaling. 3 architectures proposed, option 3 selected. 100ms latency at current spec. | 30/100 | Deprioritized | -- | Blocked on multi-GPU (needs 2-3 NVLink GPUs). Single-GPU failed. Deprioritized for this sprint per Mujtaba Jun 25.
Zone A | SCRUM-15 | TCS Cooling - DEPRIORITIZED | Thermal control system + cooling optimization research. | 20/100 | Deprioritized | -- | Secondary for this sprint. Resume when GPU infrastructure available.
-- | -- | Redeployment Decision - TBD | DVFS + cooling deprioritized. Options: (A) Eval gate testing support with Rakshit/Tilak, (B) MQTT/BACnet/Modbus protocol research for Zone B, (C) 50MW sim data prep. | -- | TBD | 2026-06-26 | DECIDE TOMORROW. Recommend Option B - Zone B protocols. Nishant overloaded, Krish has hardware/systems background.
Infra | SCRUM-35 | GCP Compute Estimate (input to Nishant) | Provide GPU compute requirements to Nishant for monthly GCP cost estimate based on DVFS work so far. | -- | TBD | 2026-06-26 | Nishant consolidates all inputs and sends to Mujtaba.